## Test cases
ID | Area | Priority | Role | Requirement | Steps | Expected result | Tester | Date | Result | Defect ID | Comments
UAT-01 | Sign-in and access | M | All | FR-AUTH-01 | Sign in to the portal / app with your account. Then sign out and try a wrong password 5 times. | Correct password signs in. After 5 wrong tries the account is locked for 15 minutes with the same message as a wrong password.
UAT-02 | Sign-in and access | M | FO | FR-AUTH-02 | Sign in on the phone, close the app, switch on airplane mode the next day and open the app. | Still signed in; animals and tasks available offline.
UAT-03 | Sign-in and access | M | FM, FO | FR-AUTH-03 | Ask HQ for the tag of an animal on another farm; search for it and scan its label. | Not shown / "This animal is not on any of your farms".
UAT-04 | Sign-in and access | M | HQ | FR-AUTH-04 | Create a field officer for Pagoh, sign in as them; then deactivate the user. | New user works on the phone; after deactivation they cannot sign in, and an open session ends within 15 minutes.
UAT-05 | Sign-in and access | S | All | FR-AUTH-01 | Change your own password (portal: your name → Change password; app: Sync → Account). | Wrong current password is refused; new password works; other devices are signed out.
UAT-06 | Sign-in and access | M | FO | FR-AUTH-03 | Open the admin portal address with a field officer account. | Access refused: field officers use the field app only.
UAT-07 | Farm and master data | M | HQ | FR-MD-01, FR-MD-02 | Add a test farm with address, area, capacity and projects EPP5 and RP4. Edit it. | Saved and listed; changes appear in the audit log.
UAT-08 | Farm and master data | M | FM | FR-MD-03 | Add groups/pens to Pagoh and put two animals in a group. | Group shown on the animal and in the animal list.
UAT-09 | Farm and master data | M | HQ | FR-MD-04, FR-MD-05 | Add a breed and a treatment product with a withdrawal period; deactivate an old product. | New items available in the app after sync; inactive product no longer offered.
UAT-10 | Farm and master data | S | HQ | FR-MD-06 | Enter feed ingredients with FELCRA's analysed values and prices. | Values used by the ration planner (UAT-37).
UAT-11 | Farm and master data | S | HQ | FR-MD-07 | Review the rule values in the HQ guide §7 with the veterinary team. | Values confirmed, or changes requested from IT (server settings, no screen).
UAT-12 | Animal registry | M | FM | FR-ANI-01, FR-ANI-03, FR-ANI-04 | Register an animal with an estimated birth date (dentition), breed, project, dam and sire. | Saved with a new animal no.; age shown with "~".
UAT-13 | Animal registry | M | FM | FR-ANI-02 | Filter Duplicate tags and Untagged; re-tag one duplicate with Change tag. | Pagoh's duplicates (107, 08478, 135, 136) and 8 untagged animals listed; old tag kept in the tag history.
UAT-14 | Animal registry | M | FM | FR-ANI-05 | Mark an animal sold, another dead, with dates and reasons. | They leave the active list, appear in the performance report's "left the herd" and in mortality.
UAT-15 | Animal registry | S | FM | FR-ANI-06 | Change a female calf to dam; look at the census history and audit log. | The census keeps the category at the time of each census; the change is in the audit log.
UAT-16 | Animal registry | M | FM | FR-ANI-07 | Print QR labels for 10 animals on sticker paper; attach and scan them at the pen. | Labels print legibly; each scan opens the right animal, also for duplicated tag numbers.
UAT-17 | Animal registry | M | FM | FR-ANI-08 | Import a census sheet with an error (two animals with the same tag, one row without category). | Preview lists the errors per row; nothing is saved until fixed; then the import succeeds.
UAT-18 | Recording at the pen (field app) | M | FO | FR-REC-01 | Scan an animal, record its weight (scale) and a weight by heart-girth tape for another. | Saved; shown in the history and in the portal's field records.
UAT-19 | Recording at the pen (field app) | M | FO | FR-REC-02 | Record BCS for 3 animals; try an impossible value. | Saved; impossible value refused with a message.
UAT-20 | Recording at the pen (field app) | S | FO | FR-REC-03 | Record milk yield for a dam (if any are milked). | Saved; appears in the lactation analysis.
UAT-21 | Recording at the pen (field app) | M | FO | FR-REC-04 | Record a vaccination with dose, route, batch and next due date. | Saved; withdrawal date shown; a task appears near the due date.
UAT-22 | Recording at the pen (field app) | S | FO | FR-REC-05 | Record an observation (legs/hooves) with two photos. | Saved; photos viewable in the portal.
UAT-23 | Recording at the pen (field app) | M | FO | FR-REC-06, FR-SYNC-01 | In airplane mode: find 5 animals, record weights, a treatment and an observation with a photo. | All saved on the phone ("will be sent when you are back online"); the pending count shows them.
UAT-24 | Recording at the pen (field app) | M | FO | FR-SYNC-02 | Switch the network back on. | Records sent automatically within a few minutes; pending count returns to 0; visible in the portal.
UAT-25 | Recording at the pen (field app) | M | FO, FM | FR-SYNC-03 | While FO is offline, FM marks one animal sold. FO records its weight offline, then goes online. | The weight is "Not accepted" with the reason; FO can discard it. Other records are not affected.
UAT-26 | Fertility and breeding | M | FO | FR-BRD-01 | Record heat for one dam, AI (with straw code) for another, natural service with a bull for a third. | Saved; status "Served"; pregnancy check task 45 days after service.
UAT-27 | Fertility and breeding | M | FO | FR-BRD-02 | Record a pregnancy check (pregnant, gestation 60 days). | Status "Pregnant"; expected calving date shown; calving task near the date.
UAT-28 | Fertility and breeding | M | FO | FR-BRD-03 | Record a calving with one calf (sex, tag, birth weight) and an assisted calving; record an abortion for another dam. | Calf registered as a new animal with its dam; events in history.
UAT-29 | Fertility and breeding | S | FO | FR-BRD-04 | Record a bull breeding soundness exam. | Saved with the result on the bull.
UAT-30 | Fertility and breeding | M | FM | FR-BRD-05 | Open Breeding; compare figures with a manual count for Pagoh. | Pregnancy rate, calving interval, calves and calving rate match the manual count.
UAT-31 | Fertility and breeding | M | FM | FR-BRD-06 | Review the culling candidates against the rules (age ≥ 8, not pregnant 12 months after calving, 2 empty checks, low BCS). | List matches the rules; reasons shown per animal; exported PDF / Excel identical.
UAT-32 | Census programme | M | FM | FR-CEN-01 | Create a census session with dates, PIC, population on record and programme treatments. | Saved and listed.
UAT-33 | Census programme | M | FM | FR-CEN-02 | Add / edit entries: weight, estimated age, remarks, selected. | Saved; selected count updates.
UAT-34 | Census programme | M | FM | FR-CEN-03 | Compare on-record vs counted per category on the session page. | Correct counts and differences (Pagoh: P 11→13, I 61→60, AJ 28→31, AB 40→36).
UAT-35 | Census programme | M | FM, HQ | FR-CEN-04 | Download the census & profiling form (PDF) for the Pagoh July 2026 session; compare with the original report. | Same layout and figures as the FFISB form; selected animals highlighted; English wording (URS question 13).
UAT-36 | Analytics | M | FM | FR-ANL-01 | Open Growth; check 3 animals in the "below the curve" list at the pen. | Curve plausible for Pagoh cattle; listed animals are indeed light for their age.
UAT-37 | Analytics | M | FM, FO | FR-ANL-03 | Plan a ration for 20 growing animals of 200 kg with FELCRA's feeds; repeat offline on the phone. | Feasible least-cost mix with cost per day; the same result offline. A nutritionist confirms it is sensible.
UAT-38 | Analytics | S | FM | FR-ANL-02 | Open Lactation (only if milk is recorded). | Curve and 305-day yield; otherwise a clear "no milk yields" message.
UAT-39 | Reminders, dashboard and reports | M | FO | FR-NOT-01 | Check the task list after UAT-21, UAT-26, UAT-27. | Treatment due, pregnancy check and calving tasks listed; overdue in red.
UAT-40 | Reminders, dashboard and reports | S | FO | FR-NOT-02 | Turn on task notifications on the phone; tap Send a test; next morning check for the task message. | Test notification arrives; morning message summarises the tasks; tapping opens the app.
UAT-41 | Reminders, dashboard and reports | M | HQ, FM | FR-RPT-01 | Compare the dashboard (all farms and Pagoh) with the animal list and breeding page. | Head counts, averages, pregnancy rate, deaths / mortality and tag problems agree.
UAT-42 | Reminders, dashboard and reports | M | FM | FR-RPT-02 | Download each report (farm performance, treatments, culling, census form, selected animals) as PDF and Excel. | Files open; figures agree with the screens; Excel suitable for further analysis.
UAT-43 | Reminders, dashboard and reports | C | HQ | FR-RPT-03 | Send me a test e-mail; after the 1st of the month check the managers' mailboxes. | E-mail with 3 PDF reports arrives; managers receive only their farms.
UAT-44 | Audit and recovery | M | HQ | FR-AUD-01 | Find in the audit log the changes made in UAT-07, UAT-13, UAT-14. | Who, when, old and new values shown for each.
UAT-45 | Audit and recovery | M | HQ | FR-AUD-02 | Delete a test animal, then restore it from Animals → Deleted animals. | Animal and its census entries back; "Deleted" and "Restored" in the audit log.

## Defects
Defect ID | Test ID | Severity | Summary | Steps / expected / actual | Reported by | Date | Status | Fixed in version | Re-tested by | Notes

## Summary
FELCRA Cattle Profiling — UAT summary
Result | All | Must
Pass
Fail
Blocked
Not run
Total
Open Critical / High defects
Exit criteria: every Must case run, no open Critical or High defects (docs/UAT.md §1).